## Sheet1
Bug_ID | Status | TC ID | Raised By | Bug Title | Steps to reproduce | Expected Result | Acutal Result | Severity | Priority | Evidence | Evidence_2 | Test Environment | Test Environment_2 | Possible Causes (Suggestions)
Bug_001 | Opened | TC_002 | Elemam Elsayed | Social Media Icons Not Working | 1- Go to the homepage"https://8pc.sa/". 2-Click on any of the social media icons (Facebook, LinkedIn, YouTube, Instagram, Twitter). | Clicking on any social media icon should open the corresponding social media page/link in a new tab or window. | The social media icons do not respond to clicks, and no links are opened. | Medium | High | https://drive.google.com/file/d/1xrGyFsN0ghIIZdeV1YsmyLWYAm5CTzge/view?usp=drive_link | https://drive.google.com/file/d/1kRBC1_5T-SmtmdVMXUu7xUigke8_wpK_/view?usp=drive_link | Device: Desktop OS: Windows 10 Pro Internet Connection: Wi-Fi Browser1: Google Chrome Version 136.0.7103.114 (Official Build) (64-bit) Browser2: Firefox Version 138.0.4 (64-bit) Browser3:Microsoft Edge Version 136.0.3240.76 (Official build) (64-bit) | Device: Samsung A30 OS: Android 11 Internet Connection: Wi-Fi Browser: Google Chrome Version 136.0.7103.125 | Missing or incorrect href links in the anchor tags. JavaScript event prevents the default action. Icons are implemented as static images with no clickable functionality.
Bug_002 | Suggestion | TC_008 | Elemam Elsayed | "الملف التعريفي" Button Scrolls to Top While Already at Top | 1- Go to "https://8pc.sa/%d9%85%d9%86-%d9%86%d8%ad%d9%86//". 2-Locate the "من نحن" button at the top of the page 3-Click the button while still at the top |  | The page scrolls slightly to the top again, with no visible content change or new section shown. | Low | Medium | https://drive.google.com/file/d/1P2o46JM2-GQYve7Gdr7WZDUa0GEqWyE3/view?usp=drive_link |  | Device: Desktop OS: Windows 10 Pro Internet Connection: Wi-Fi Browser1: Google Chrome Version 136.0.7103.114 (Official Build) (64-bit) Browser2: Firefox Version 138.0.4 (64-bit) Browser3:Microsoft Edge Version 136.0.3240.76 (Official build) (64-bit) | Device: Samsung A30 OS: Android 11 Internet Connection: Wi-Fi Browser: Google Chrome Version 136.0.7103.125 | Update the button to: Scroll to a specific "Company Profile" section with meaningful content further down the page or Link to a downloadable company profile PDF file or Hide or disable the button when already at the top to avoid confusion
Bug_003 | Opened | TC_009 | Elemam Elsayed | Company Introduction Video Displays Irrelevant Content | 1- Go to "https://8pc.sa/%d9%85%d9%86-%d9%86%d8%ad%d9%86//". 2-Scroll to the section that contains the company introduction video 3-Watch the video content | The video should display relevant, branded content clearly introducing the company, its services, mission, or team It should help users understand who the company is. | The video content is unrelated to the company, its values, services, or team. No company branding, message, or relevant visuals are present. | High | High | https://drive.google.com/file/d/1NfQiZnya5WcmdmYFZ623TetSO8fCbjqi/view?usp=drive_link | https://drive.google.com/file/d/1ighY5nJGXkxi6dIS_qwImNj2wM-vRSAp/view?usp=drive_link | Device: Desktop OS: Windows 10 Pro Internet Connection: Wi-Fi Browser1: Google Chrome Version 136.0.7103.114 (Official Build) (64-bit) Browser2: Firefox Version 138.0.4 (64-bit) Browser3:Microsoft Edge Version 136.0.3240.76 (Official build) (64-bit) | Device: Samsung A30 OS: Android 11 Internet Connection: Wi-Fi Browser: Google Chrome Version 136.0.7103.125 | Replace the current video with an accurate and official company introduction video Ensure the new video includes branding, accurate messaging, and aligns with the company’s purpose.
Bug_004 | Opened | TC_012 | Elemam Elsayed | The "الاستشارات " dropdown menu opens, but when clicking any option, only the last option is activated | 1- Go to the homepage"https://8pc.sa/". 2-Click on the arrow to open the dropdown "الاستشارات ". 3-Click on any option in the list. 4- Only the last option is activated regardless of the clicked choice. | Each option in the "الاستشارات " dropdown should activate individually when selected. | Clicking any option always activates only the last option in the dropdown list. | Medium | Low | https://drive.google.com/file/d/1cBfrRDVD0HJ1slOwqDzNpttiaOUeTDjN/view?usp=drive_link | https://drive.google.com/file/d/1iRVM2uAz8kmIxRhQ5U0yXjQEfRWqhitB/view?usp=drive_link | Device: Desktop OS: Windows 10 Pro Internet Connection: Wi-Fi Browser1: Google Chrome Version 136.0.7103.114 (Official Build) (64-bit) Browser2: Firefox Version 138.0.4 (64-bit) Browser3:Microsoft Edge Version 136.0.3240.76 (Official build) (64-bit) | Device: Samsung A30 OS: Android 11 Internet Connection: Wi-Fi Browser: Google Chrome Version 136.0.7103.125 | Check the event handler code. Ensure each option has a unique identifier or value.
Bug_005 | Opened | TC_056 | Elemam Elsayed | Placeholder text remains inside multiple input fields in the "تواصل معنا" form. | 1- Go to the "https://8pc.sa/consultation/%d8%a7%d9%84%d8%aa%d8%b3%d9%88%d9%8a%d9%82-%d8%a7%d9%84%d8%b1%d9%82%d9%85%d9%8a/". 2- Click the "الاسم "input field. 3-Start typing a name, e.g., "الامام". | The placeholder text "أدخل أسمك" should disappear when the user starts typing, and only the user's input should be visible. | The placeholder text "أدخل أسمك" stays in the input field and becomes part of the text. | High | Medium | https://drive.google.com/file/d/1Wscrl3fH_WpxRHBU1qfFwOFlZvjA74QG/view?usp=drive_link | https://drive.google.com/file/d/1DCV_ANHdi7ew9uDTDVXRoPTlo-ejTCAs/view?usp=drive_link | Device: Desktop OS: Windows 10 Pro Internet Connection: Wi-Fi Browser1: Google Chrome Version 136.0.7103.114 (Official Build) (64-bit) Browser2: Firefox Version 138.0.4 (64-bit) Browser3:Microsoft Edge Version 136.0.3240.76 (Official build) (64-bit) | Device: Samsung A30 OS: Android 11 Internet Connection: Wi-Fi Browser: Google Chrome Version 136.0.7103.125 | Placeholder text implemented incorrectly (e.g., as a default value instead of using the placeholder. Ensure the input field uses the HTML placeholder attribute.
Bug_006 | Opened | TC_057 | Elemam Elsayed | "Contact Us" form allows submission without selecting "نوع الاستشارة المطلوبة" | 1- Go to the "https://8pc.sa/consultation/%d8%a7%d9%84%d8%aa%d8%b3%d9%88%d9%8a%d9%82-%d8%a7%d9%84%d8%b1%d9%82%d9%85%d9%8a/". 2- Fill out all fields except the "نوع الاستشارة المطلوبة" dropdown. 3-Click the "إرسال" button. | The form should not submit unless a valid option is selected from the "نوع الاستشارة المطلوبة" dropdown. | The form submits successfully even when "نوع الاستشارة المطلوبة" is not selected. No error message appears to alert the user. | High | High | https://drive.google.com/file/d/136abstFIGz7W0QFcuVC1lRe8LcrOuLih/view?usp=drive_link | https://drive.google.com/file/d/1i_psPZJw0T9YBAhJPXRIsWtu5hMGUwov/view?usp=drive_link | Device: Desktop OS: Windows 10 Pro Internet Connection: Wi-Fi Browser1: Google Chrome Version 136.0.7103.114 (Official Build) (64-bit) Browser2: Firefox Version 138.0.4 (64-bit) Browser3:Microsoft Edge Version 136.0.3240.76 (Official build) (64-bit) | Device: Samsung A30 OS: Android 11 Internet Connection: Wi-Fi Browser: Google Chrome Version 136.0.7103.125 | The dropdown field is missing the required attribute. Validation is not implemented for this field.
Bug_007 | Opened | TC_067 | Elemam Elsayed | "نموذج الاتصال لمشاركة التفاصيل الخاصة" form submits even when the "الاسم" field is left empty | 1- Go to the "https://8pc.sa/%d8%aa%d9%88%d8%a7%d8%b5%d9%84-%d9%85%d8%b9%d8%a7%d9%86%d8%a7/". 2-Leave the "الاسم" field completely empty. 3-Fill in other fields (email, message, type of inquiry, etc.) with valid data 4-Click the "إرسال" button. | The form should not be submitted. A validation message should appear, such as: "يرجى إدخال الاسم". Focus should return to the "Name" field for user correction. | The form submits successfully even though the "Name" field is empty. No validation error is displayed. | High | High | https://drive.google.com/file/d/1sG4YwGQZV3ARfADtnElzI_hvA_UzLPeV/view?usp=drive_link | https://drive.google.com/file/d/1I5RsHXeLw_-vfMvl1_NsYpFrv1wcbfw7/view?usp=drive_link | Device: Desktop OS: Windows 10 Pro Internet Connection: Wi-Fi Browser1: Google Chrome Version 136.0.7103.114 (Official Build) (64-bit) Browser2: Firefox Version 138.0.4 (64-bit) Browser3:Microsoft Edge Version 136.0.3240.76 (Official build) (64-bit) | Device: Samsung A30 OS: Android 11 Internet Connection: Wi-Fi Browser: Google Chrome Version 136.0.7103.125 | Add client-side validation (required attribute in HTML or JS check). Ensure server-side validation also rejects submissions with a missing name. Placeholder text ("ادخل الاسم") should not act as value content.
Bug_008 | Opened | TC_068 | Elemam Elsayed | "نموذج الاتصال لمشاركة التفاصيل الخاصة" form submits even when the "الرسالة" field is left empty | 1- Go to the "https://8pc.sa/%d8%aa%d9%88%d8%a7%d8%b5%d9%84-%d9%85%d8%b9%d8%a7%d9%86%d8%a7/". 2-Leave the "الرسالة" field completely empty. 3-Fill in other fields (email, Name, type of inquiry, etc.) with valid data 4-Click the "إرسال" button. | The form should not be submitted. A validation message should appear, such as: "يرجى إدخال رسالة". Focus should return to the "الرسالة" field for user correction. | The form is submitted even when the "الرسالة" field is blank. No error message is displayed. | High | High | https://drive.google.com/file/d/1U2o5KwYpigzISiHPuix7KW_c6kznmFCQ/view?usp=drive_link | https://drive.google.com/file/d/1TIVF7R8S--nr48miYIAdUFIqexMcyNIB/view?usp=drive_link | Device: Desktop OS: Windows 10 Pro Internet Connection: Wi-Fi Browser1: Google Chrome Version 136.0.7103.114 (Official Build) (64-bit) Browser2: Firefox Version 138.0.4 (64-bit) Browser3:Microsoft Edge Version 136.0.3240.76 (Official build) (64-bit) | Device: Samsung A30 OS: Android 11 Internet Connection: Wi-Fi Browser: Google Chrome Version 136.0.7103.125 | Add client-side validation (required attribute in HTML or JS check). Ensure server-side validation also rejects submissions with a missing message. Placeholder text ("ادخل الرسالة") should not act as value content.
Bug_009 | Opened | TC_064 | Elemam Elsayed | Nonsensical text displayed in the "النشرة الإخبارية" section | 1- Go to the "https://8pc.sa/%d9%85%d8%a7%d9%87%d9%8a-%d8%a7%d9%87%d9%85%d9%8a%d8%a9-%d8%a7%d9%84%d8%a7%d9%85%d9%86-%d8%a7%d9%84%d8%b3%d9%8a%d8%a8%d8%b1%d8%a7%d9%86%d9%8a%d8%9f-%d8%af%d9%84%d9%8a%d9%84-%d8%b4%d8%a7%d9%85%d9%84/". 2-Scroll to the Bottom of the Page 3- Observe the text under the"النشرة الإخبارية" Section | The text should be meaningful, such as: "اشترك في النشرة الإخبارية لدينا للحصول على آخر التحديثات والنصائح." | Text displayed:"أبجد هوزحطي كلمن سعفص قرشت نخذ ضظغ" The text is: Nonsensical/meaningless Contains random letters that do not form valid Arabic words | Low | Medium | https://drive.google.com/file/d/1wJmTMsrL8CPUJ_uSk_mSqpyMbER4xkeD/view?usp=drive_link | https://drive.google.com/file/d/15xHdrIVMbUh9gbXan-nIAIXgA2IuzihQ/view?usp=drive_link | Device: Desktop OS: Windows 10 Pro Internet Connection: Wi-Fi Browser1: Google Chrome Version 136.0.7103.114 (Official Build) (64-bit) Browser2: Firefox Version 138.0.4 (64-bit) Browser3:Microsoft Edge Version 136.0.3240.76 (Official build) (64-bit) | Device: Samsung A30 OS: Android 11 Internet Connection: Wi-Fi Browser: Google Chrome Version 136.0.7103.125 | Replace the current text with relevant content inviting users to subscribe.
Bug_010 | Opened | TC_003 | Elemam Elsayed | First content image on homepage appears cropped on mobile devices | 1- Go to the homepage"https://8pc.sa/". 2-Scroll to the first image displayed below the main header 3-Observe the way the image appears (cropped, zoomed in) 4-Compare with the view on a desktop browser | The image should scale proportionally and be fully visible on mobile devices without cutting off any parts. | The image appears cropped or zoomed in on mobile devices. Some parts of the image are not visible or cut off, affecting the content presentation | Medium | High | N/A | https://drive.google.com/file/d/1xxt6TCoM4qearBs8w36vBddYEik9PRSN/view?usp=drive_link | N/A | Device: Samsung A30 OS: Android 11 Internet Connection: Wi-Fi Browser: Google Chrome Version 136.0.7103.125 | Ensure image uses: Review media queries for mobile layout Check if the container has overflow or height restrictions